## Task Plan
Health Docket — Repo Restructuring Gantt
Edit yellow cells only: Status, and Duration/Manual Start where shown. Everything else recalculates. Task list/phases/dependencies from policy-docket-design-spec.docx §8 (spec of record); durations are Claude's estimates, not from the spec.
Project Start Date | 2026-09-22
As of / today | 2026-09-19
ID | Task | Phase | Status | Predecessor(s) | Duration (days, Claude's estimate) | Start Offset | End Offset | Start Date | End Date | Files this task creates/changes | Notes | Design reference (policy-docket-design-spec.docx) | Verify done (run this yourself)
1 | Design & migrate schema | Foundation | In progress | — | 7 | 0 | 6 | 2026-09-22 | 2026-09-28 | db/schema.sql; db/migrate_from_json.py; db/docket.sqlite (generated) | Already started: db/schema.sql and db/migrate.py exist in the repo as of 2026-09-19. | Spec §4 Data Model — column-level detail for bodies/meetings/meeting_documents/meeting_subjects, plus the full 11-table schema in §4 of the earlier system-design.docx. | Run the migration script; row counts in the new tables must match meetings.json/briefing.json exactly, and every meeting_id/body_id foreign key must resolve — no orphans.
2 | Verify Legistar API access (nnph-dboh) | Foundation | Not started | — | 3 | 0 | 2 | 2026-09-22 | 2026-09-24 | scrapers/legistar.py | Also fix the nnph-dboh body_name bug found 2026-09-19: config says 'District Board of Health', the live Legistar site says 'Northern Nevada Public Health'. Spec §10 flags this as an open risk ("Legistar API access unconfirmed... org-level network/domain-allowlist question"). | Spec §10 Risks & Open Questions — "Legistar API access unconfirmed" row; scrapers/legistar.py already has the webapi.legistar.com attempt + HTML fallback. | Call webapi.legistar.com/v1/washoe/events directly; confirm it returns real event JSON, not an error. If it fails, run the HTML-fallback path in legistar.py and confirm it returns real meetings for 'Northern Nevada Public Health' (not zero, per the body_name bug above).
3 | Harden NELIS scraper selectors | Foundation | Not started | — | 4 | 0 | 3 | 2026-09-22 | 2026-09-25 | scrapers/nelis.py | Repo's own docstring calls this 'the least-tested scraper' — selectors were written blind, never verified against the live site. | Spec §10 Risks & Open Questions — "NELIS selectors unverified... Open — Task 3 in the build plan." | Run scrapers/nelis.py against the live leg.state.nv.us site; confirm it returns real meeting rows for the Joint Interim Standing Committee on Health & Human Services, not an empty list.
4 | Provision hosting | Foundation | Not started | — | 4 | 3 | 6 | 2026-09-25 | 2026-09-28 | deploy/render.yaml (or fly.toml); deploy/.env.example | The one task where Jack creates the account/billing — not something Claude can do. | Spec §9.3 Rough cost estimate — hosting ~$5-10/mo (Render, Railway, Fly.io, or a cheap VPS). | Hit the hosted app's URL from a browser with no VPN, on a different network than Jack's Mac; confirm it actually responds, not just reachable on localhost.
5 | Backend API | Backend/Frontend | Not started | T1 | 10 | 7 | 16 | 2026-09-29 | 2026-10-08 | api/main.py; api/db.py; api/routes/policy_areas.py; api/routes/health.py; api/routes/subjects.py; api/routes/focus_areas.py | Needs the schema from Task 1. Seven endpoints per spec §6. | Spec §6 API Specification — 7 endpoints: GET /api/policy-areas, GET /api/policy-areas/{slug}/snapshot, /attention, /bodies, GET /api/subjects/{slug}, GET+POST /api/focus-areas. Every read endpoint returns {data, generated_at}; AI-derived fields nest under model_version (spec §6, NFR3). | curl each of the 7 endpoints in spec §6 against the running API; confirm each returns the documented JSON envelope {data, generated_at} and the correct error code (404/400) for bad input.
6 | Document capture pipeline | Data pipeline | Not started | T1, T2, T3 | 10 | 7 | 16 | 2026-09-29 | 2026-10-08 | pipeline/capture_documents.py | Per spec §8, this depends on the schema AND both scraper-verification tasks — not just the schema — since it needs confirmed-working scrapers to know which documents are even reachable. | Spec §9.2 pipeline stage table, row 'Capture documents': input = meeting_documents rows with a source_file_url, output = files downloaded + capture_status updated, failure = a 404/auth wall sets capture_status back to not_linked with a logged reason. | Query meeting_documents after a run; confirm capture_status has moved past 'not_linked' for at least one meeting with a known real agenda/minutes URL, and that the file actually downloaded.
7 | Extraction pipeline (OCR + LLM) | Data pipeline | Not started | T6 | 7 | 17 | 23 | 2026-10-09 | 2026-10-15 | pipeline/extract_text.py | Needs captured documents from Task 6. | Spec §9.2 pipeline stage table, row 'Extract': input = captured files, output = extracted_text + extraction_status, failure = OCR/LLM failure sets extraction_status='failed', keeps prior state. | Query a captured meeting's extracted_text column; confirm it holds real text pulled from the actual file, not null/empty, and extraction_status = success.
8 | Subject tagging (LLM) | Data pipeline | Not started | T7 | 7 | 24 | 30 | 2026-10-16 | 2026-10-22 | pipeline/tag_subjects.py | Needs extracted text from Task 7. | Spec §4.1 meeting_subjects table (meeting_id, subject_id, confidence, tagged_by) + §9.2 pipeline stage 'Tag subjects': below-threshold confidence is stored and surfaced, never discarded. | Query meeting_subjects for a known meeting (e.g. the House E&C Medicaid hearing already in the repo); confirm a real subject_id and confidence score, tagged_by='ai' — not the old body-level admin tag standing in for it.
9 | Briefing generation upgrade | Data pipeline | Not started | T8 | 3 | 31 | 33 | 2026-10-23 | 2026-10-25 | pipeline/generate_briefings.py | Needs real subject tags from Task 8. | Spec §9.2 pipeline stage table, row 'Generate briefings': input = extracted_text + meeting_subjects, output = briefings rows with model_version. | Check briefings for that same meeting; confirm the note text reflects the actual extracted agenda/minutes content, not just the meeting title the way the current generator does.
10 | Frontend cutover to live API | Launch | Not started | T5, T9, T4 | 10 | 34 | 43 | 2026-10-26 | 2026-11-04 | templates/overview.html.j2; templates/health.html.j2; templates/subject.html.j2; static/docket.css; static/docket.js; .github/workflows/weekly-refresh.yml; README.md; retires data/*.json and scripts/render_site.py | Per spec §8, this is the single final task — ports the prototype's screens to the live API AND cuts over hosting/CI in one step, rather than two separate tasks. | Spec §7 Frontend Implementation Approach + §6 (swap each screen's hardcoded JS array for a fetch() call to its matching endpoint). | Open the live hosted site; confirm the Medicaid subject page pulls from the real API (Network tab shows a fetch to /api/subjects/medicaid, not a hardcoded array) and the Overview grid's counts match a direct query against the database.
Phase legend: | Foundation | Data pipeline | Backend/Frontend | Launch
Session log — append one row per session, don't overwrite prior rows
Date | What changed | Task status changes
2026-09-19 | Rebuilt this Task Plan's 10 rows to match policy-docket-design-spec.docx §8 Build Plan (previously based on the outdated “Docket Build Map” artifact, which used a different task split and dependency set). Added the Design reference and Verify done columns. | No task status changed by this rebuild. Task 1 remains In progress (unchanged from prior session).
Formulas:
Start Date = B4+[Start Offset]
End Date = B4+[End Offset]

## Gantt
Health Docket — Gantt (auto-updates from Task Plan)
Change dates/durations/status on the Task Plan tab — this chart redraws itself.
ID | Task (status) | Phase | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | StartOff | EndOff
 | time axis 2026-09-22 to 2026-11-04
1 | Design & migrate schema [In progress] | Foundation | [44 empty] | 0 | 6
2 | Verify Legistar API access (nnph-dboh) [Not started] | Foundation | [44 empty] | 0 | 2
3 | Harden NELIS scraper selectors [Not started] | Foundation | [44 empty] | 0 | 3
4 | Provision hosting [Not started] | Foundation | [44 empty] | 3 | 6
5 | Backend API [Not started] | Backend/Frontend | [44 empty] | 7 | 16
6 | Document capture pipeline [Not started] | Data pipeline | [44 empty] | 7 | 16
7 | Extraction pipeline (OCR + LLM) [Not started] | Data pipeline | [44 empty] | 17 | 23
8 | Subject tagging (LLM) [Not started] | Data pipeline | [44 empty] | 24 | 30
9 | Briefing generation upgrade [Not started] | Data pipeline | [44 empty] | 31 | 33
10 | Frontend cutover to live API [Not started] | Launch | [44 empty] | 34 | 43
Phase legend: | Foundation | Data pipeline | 2026-09-22: Backend/Frontend; 2026-09-23: Launch